## GCS Requirements
Requirement ID | Requirement | Category | Allocation | Verification Package | Method | Level | Procedure | Test Case | Evidence | Acceptance Criteria | Status
STK-008 | The system shall be transportable by one person. | Stakeholder | Mechanical | GCS Verification | Inspection | System | TP-001 | TC-MNT-001 | VE-001 | One person can lift, carry, and deploy the transport configuration without disassembly beyond normal setup actions. | Planned
SYS-INT-003 | The system shall support Ethernet communications. | Interface | GCS Communications | GCS Verification | Test | Subsystem | TP-011 | TC-INT-003 | VE-001 | The GCS establishes Ethernet connectivity and successfully transfers data. | Planned
SYS-INT-004 | The system shall support USB peripheral connections. | Interface | GCS Interfaces | GCS Verification | Test | Subsystem | TP-011 | TC-INT-004 | VE-001 | Configured USB peripherals enumerate and operate without errors. | Planned
SYS-ENV-004 | The system shall tolerate transportation-induced vibration. | Environmental | Mechanical | GCS Verification | Test | Assembly | TP-007 | TC-ENV-004 | VE-006 | After the transportation-vibration profile, hardware remains secure and passes post-test functional checks. | Planned
SYS-SEC-001 | The system shall authenticate operator access. | Security | Cybersecurity | GCS Verification | Test | System | TP-010 | TC-SEC-001 | VE-005 | Protected operator functions are unavailable until valid authentication is completed. | Planned
SYS-SEC-002 | The system shall protect mission data. | Security | Cybersecurity/Data | GCS Verification | Inspection | System | TP-010 | TC-SEC-002 | VE-005 | Configured operating-system or application controls restrict unauthorized mission-data modification. | Planned
SYS-SEC-004 | The system shall maintain audit logs of mission activities. | Security | Cybersecurity/Data | GCS Verification | Test | System | TP-010 | TC-SEC-004 | VE-005 | Configured mission and access events appear in the audit log with usable timestamps. | Planned
SYS-MIS-005 | The system shall display the planned flight route to the operator. | Mission Management | GCS/HMI | GCS Verification | Demonstration | System | TP-011 | TC-MIS-006 | VE-002 | The complete planned route is displayed on the GCS map before launch. | Planned
SYS-DAT-003 | The system shall assign a unique identifier to each mission data set. | Data Management | Data Management | GCS Verification | Test | System | TP-002 | TC-DAT-005 | VE-002 | Each generated mission data set has a unique identifier not reused by another data set. | Planned
SYS-DAT-004 | The system shall preserve recorded mission data following a normal system shutdown. | Data Management | Data Management | GCS Verification | Test | System | TP-002 | TC-DAT-006 | VE-002 | Recorded mission data remains intact and readable after normal shutdown and restart. | Planned
SYS-DAT-005 | The system shall permit authorized users to retrieve recorded mission data after mission completion. | Data Management | Data Management | GCS Verification | Demonstration | System | TP-002 | TC-DAT-007 | VE-002 | An authenticated user retrieves the selected completed-mission data set. | Planned
SYS-GCS-002 | The GCS shall display vehicle position on a digital map. | GCS | GCS/HMI | GCS Verification | Test | System | TP-011 | TC-GCS-004 | VE-002 | The vehicle position symbol is displayed and updates on the digital map. | Planned
SYS-GCS-003 | The GCS shall display vehicle altitude, heading, speed, and flight mode. | GCS | GCS/HMI | GCS Verification | Test | System | TP-011 | TC-GCS-005 | VE-002 | Altitude, heading, speed, and flight mode are simultaneously displayed and update during operation. | Planned
SYS-GCS-004 | The GCS shall display battery status and available system-health information. | GCS | GCS/HMI | GCS Verification | Test | System | TP-011 | TC-GCS-006 | VE-002 | Battery and configured system-health indicators are visible and update during operation. | Planned
SYS-PWR-006 | The system shall prevent reverse-polarity connection at externally accessible power interfaces through connector design or protective circuitry. | Power | Power Safety | GCS Verification | Inspection | Component | TP-012 | TC-PWR-006 | VE-001 | Connector keying or protective circuitry prevents damaging current flow under reversed-polarity test conditions. | Planned
SYS-HMI-001 | The system shall present critical warnings in a visually distinguishable format. | HMI | HMI | GCS Verification | Demonstration | System | TP-011 | TC-HMI-002 | VE-002 | Critical warnings are visually distinct from normal status and advisory information. | Planned
SYS-HMI-002 | The system shall identify the current vehicle flight mode to the operator. | HMI | HMI | GCS Verification | Test | System | TP-011 | TC-HMI-003 | VE-002 | The displayed flight mode matches the active vehicle mode during each test transition. | Planned
SYS-HMI-003 | The system shall display the status of the command-and-control link. | HMI | HMI | GCS Verification | Test | System | TP-011 | TC-HMI-004 | VE-003 | The command-and-control link status changes correctly for connected, degraded, and lost conditions. | Planned
SYS-HMI-004 | The system shall display the status of the telemetry link. | HMI | HMI | GCS Verification | Test | System | TP-011 | TC-HMI-005 | VE-003 | The telemetry-link status changes correctly for connected, degraded, and lost conditions. | Planned
SYS-HMI-005 | The system shall display the status of the live-video link. | HMI | HMI | GCS Verification | Test | System | TP-011 | TC-HMI-006 | VE-003 | The live-video link status changes correctly for connected, degraded, and lost conditions. | Planned
SYS-HMI-006 | The system shall require operator confirmation before executing a mission-termination command. | HMI | HMI/Safety | GCS Verification | Test | System | TP-011 | TC-HMI-007 | VE-002 | A mission-termination command is not executed until the operator completes the confirmation action. | Planned
SYS-MNT-004 | The system shall provide externally visible identification for major electrical interfaces. | Maintainability | Maintainability | GCS Verification | Inspection | Component | TP-001 | TC-MNT-005 | VE-001 | All designated major external electrical interfaces have legible identification. | Planned
SYS-MNT-006 | The system shall permit inspection of major structural and electrical connections during scheduled maintenance. | Maintainability | Maintainability | GCS Verification | Inspection | Assembly | TP-001 | TC-MNT-007 | VE-001 | All designated major structural and electrical connections are accessible for visual inspection. | Planned
SYS-CYB-001 | The system shall restrict administrative configuration functions to authorized users. | Cybersecurity | Cybersecurity | GCS Verification | Test | System | TP-010 | TC-CYB-001 | VE-005 | Unauthorized users cannot access administrative configuration functions. | Planned
SYS-CYB-002 | The system shall require authentication before access to protected GCS functions. | Cybersecurity | Cybersecurity | GCS Verification | Test | System | TP-010 | TC-CYB-002 | VE-005 | Protected GCS functions remain inaccessible until valid authentication is completed. | Planned
SYS-CYB-003 | The system shall protect stored mission data from unauthorized modification using available operating-system or application controls. | Cybersecurity | Cybersecurity/Data | GCS Verification | Test | System | TP-010 | TC-CYB-003 | VE-005 | An unauthorized account cannot modify protected stored mission data. | Planned
SYS-CYB-006 | The system shall record security-relevant access or configuration events when supported by the selected software. | Cybersecurity | Cybersecurity | GCS Verification | Test | System | TP-010 | TC-CYB-006 | VE-005 | Configured access and configuration events are recorded with event type and timestamp. | Planned