## GCS Verification Matrix
Requirement ID | Requirement | Verification Method | Verification Level | Test Procedure | Test Activity | Verification Evidence | Status | Test Report
GCS-FUN-001 | Initialize required mission software prior to flight. | Test | Subsystem | TP-002 | Functional Bench Startup | Startup screenshots | Planned | TR-002
GCS-FUN-002 | Support mission planning and configuration. | Demonstration | Subsystem | TP-011 | Mission Planning Demonstration | Mission file/screenshots | Planned | TR-011
GCS-FUN-003 | Display aircraft telemetry during mission execution. | Test | Integration | TP-004 | Telemetry Monitoring | Telemetry log | Planned | TR-004
GCS-FUN-004 | Transmit operator commands to the aircraft. | Test | Integration | TP-003 | Ground Integration | MAVLink command log | Planned | TR-003
GCS-FUN-005 | Display payload imagery received from the aircraft. | Demonstration | Subsystem | TP-011 | Payload Display | Display screenshots | Planned | TR-011
GCS-COM-001 | Establish bidirectional telemetry communications. | Test | Integration | TP-004 | Communication Link Test | Connection log | Planned | TR-004
GCS-COM-002 | Recover communications following telemetry interruption. | Test | Integration | TP-004 | Link Recovery | Recovery log | Planned | TR-004
GCS-HMI-001 | Provide an integrated operator workstation. | Inspection | Subsystem | TP-011 | Operator Workstation Inspection | Photographs | Planned | TR-011
GCS-HMI-002 | Support keyboard and pointing-device input. | Test | Subsystem | TP-011 | Operator Input Verification | Photos/video | Planned | TR-011
GCS-PWR-001 | Operate using an internal rechargeable battery. | Test | Subsystem | TP-002 | Battery Operation | Voltage/runtime data | Planned | TR-002
GCS-PWR-002 | Provide fused and regulated electrical power. | Inspection/Test | Subsystem | TP-011 | Power Distribution Verification | Voltage measurements | Planned | TR-011
GCS-MEC-001 | Utilize a portable protective enclosure. | Inspection | Subsystem | TP-011 | Mechanical Inspection | Photographs | Planned | TR-011
GCS-MEC-002 | Securely mount internal hardware. | Inspection | Subsystem | TP-011 | Hardware Inspection | Photographs | Planned | TR-011
GCS-INT-001 | Interface with the UAV flight controller. | Test | Integration | TP-003 | Flight Controller Integration | MAVLink status | Planned | TR-003
GCS-INT-002 | Interface with the telemetry subsystem. | Test | Integration | TP-004 | Telemetry Interface | Connection log | Planned | TR-004
GCS-SW-001 | Operate using a Linux-based operating system. | Test | Subsystem | TP-002 | Operating System Verification | Boot log | Planned | TR-002
GCS-SW-002 | Support QGroundControl mission software. | Test | Subsystem | TP-002 | QGroundControl Verification | Application screenshots | Planned | TR-002
GCS-SAF-001 | Incorporate overcurrent protection. | Inspection | Subsystem | TP-011 | Electrical Safety Inspection | Photographs | Planned | TR-011
GCS-SAF-002 | Provide safe removal of electrical power. | Test | Subsystem | TP-011 | Shutdown Verification | Shutdown checklist | Planned | TR-011